## excel
Fecha Planeada de FinalizaciÃ³n: | 2014-04-29
Fecha replaneada de FinalizaciÃ³n: | 2014-05-05
VariaciÃ³n del Costo: | 2.148 | (2,15 horas debajo de presupuesto)
% VariaciÃ³n del Costo: | 4% | (4% debajo de presupuesto)
Ãndice del Costo de DesempeÃ±o(CPI): | 1.045
VariaciÃ³n del Calendario: | 0 | (0 minutos adelante del calendario)
% VariaciÃ³n del Calendario: | 0% | (0% adelante del calendario)
VariaciÃ³n planeada de duraciÃ³n: | 0 | (0 minutos adelante del calendario)
Ãndice de DesempeÃ±o de Calendario: | 1
Porcentaje Completado: | 100%
Porcentaje Utilizado: | 96%
Ãndice de DesempeÃ±o para Completar: | 0
Factor de Mejoramiento: | -1
PronÃ³stico de Costo: | 47.433 | (47,4 horas)
PronÃ³stico cuanto durarÃ¡ el proyecto: | 61.527 | (2,05 mes)
Fecha Pronosticada de FinalizaciÃ³n: | 2014-05-05
Proyecto/Tarea | Tipo | PT | Tiempo | PV | Fecha Planeada | Replaneada | ProyecciÃ³n | Fecha | Etiquetas | Dep | %C | %U | VG(EV)
/Process Dashboard/ChangeCounter/Ciclo1/Launch/INFOForm | Misc | 0.16597 | 0.0069444 | 8% | 2014-03-18 | 2014-04-02 | 2014-04-02 | 2014-04-02 | LAU1 | Otros interesados | 100% | 4% | 8%
/Process Dashboard/ChangeCounter/Ciclo1/Strategy/Configuration plan | Strategy | 0.16806 | 0.041667 | 8.2% | 2014-03-25 | 2014-04-02 | 2014-04-02 | 2014-04-02 | STRAT1 | Esperando | 100% | 25% | 8.2%
/Process Dashboard/ChangeCounter/Ciclo1/Reqts/SRS | Reqts Review | 0.035417 | 0.013889 | 1.7% | 2014-03-25 | 2014-04-02 | 2014-04-02 | 2014-04-02 | REQ1 | Otros interesados | 100% | 40% | 1.7%
/Process Dashboard/ChangeCounter/Ciclo1/Design/SDS Baseline | Design | 0.059722 | 0.027778 | 2.9% | 2014-03-25 | 2014-04-02 | 2014-04-02 | 2014-04-02 | DES1 | Otros interesados | 100% | 46% | 2.9%
/Process Dashboard/ChangeCounter/Ciclo1/Planning/Personal TASK | Planning | 0.0055556 | 0.041667 | 0.3% | 2014-03-25 | 2014-04-02 | 2014-04-02 | 2014-04-02 | PLAN1 | Otros interesados | 100% | 777% | 0.3%
/Process Dashboard/ChangeCounter/Ciclo1/Planning/Personal SCHEDULE | Planning | 0.0055556 | 0.013889 | 0.3% | 2014-03-25 | 2014-04-02 | 2014-04-02 | 2014-04-02 | PLAN1 | Otros interesados | 100% | 259% | 0.3%
/Process Dashboard/ChangeCounter/Ciclo1/Documentation/OutLine | Documentation | 0.10208 | 0.29167 | 4.9% | 2014-04-01 | 2014-04-09 | 2014-04-09 | 2014-04-09 |  |  | 100% | 286% | 4.9%
/Process Dashboard/ChangeCounter/Ciclo1/Every Week/weekly meeting | Postmortem | 0.011806 | 0.083333 | 0.6% | 2014-04-01 | 2014-04-09 | 2014-04-09 | 2014-04-09 |  |  | 100% | 724% | 0.6%
/Process Dashboard/ChangeCounter/Ciclo1/Every Week/Data reporting | Postmortem | 0.0055556 | 0.00625 | 0.3% | 2014-04-01 | 2014-04-09 | 2014-04-09 | 2014-04-09 |  |  | 100% | 116% | 0.3%
/Process Dashboard/ChangeCounter/Ciclo1/Documentation/Review | Documentation | 0.011111 | 0 | 0.5% | 2014-04-01 | 2014-04-09 | 2014-04-09 | 2014-04-09 |  |  | 100% |  | 0.5%
/Process Dashboard/ChangeCounter/Ciclo1/Code/Detailed Design | Design | 0.0048611 | 0.020833 | 0.2% | 2014-04-01 | 2014-04-09 | 2014-04-09 | 2014-04-09 | IMP1 | Otros interesados | 100% | 408% | 0.2%
/Process Dashboard/ChangeCounter/Ciclo1/Code/Implementation | Code | 0.11667 | 0.1875 | 5.6% | 2014-04-01 | 2014-04-09 | 2014-04-09 | 2014-04-09 | IMP1 | Otros interesados | 100% | 161% | 5.6%
/Process Dashboard/ChangeCounter/Ciclo1/Code/Code Review | Code Review | 0.058333 | 0.0069444 | 2.8% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | IMP1 | Otros interesados | 100% | 12% | 2.8%
/Process Dashboard/ChangeCounter/Ciclo1/Code/UpdateLOGD | Code Inspect | 0.0020833 | 0.0069444 | 0.1% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | IMP1 | Otros interesados | 100% | 286% | 0.1%
/Process Dashboard/ChangeCounter/Ciclo1/Code/UpdateLOGT | Code Inspect | 0.0020833 | 0.0069444 | 0.1% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | IMP1 | Otros interesados | 100% | 286% | 0.1%
/Process Dashboard/ChangeCounter/Ciclo1/Code/Unit Test | Test | 0.0090278 | 0.0069444 | 0.4% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | IMP1 | Otros interesados | 100% | 79% | 0.4%
/Process Dashboard/ChangeCounter/Ciclo1/Test/Sys Test | Sys Test | 0.00625 | 0.0069444 | 0.3% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | TEST1 | Otros interesados | 100% | 107% | 0.3%
/Process Dashboard/ChangeCounter/Ciclo1/Test/Int Test | Int Test | 0.00625 | 0.0034722 | 0.3% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | TEST1 | Esperando | 100% | 54% | 0.3%
/Process Dashboard/ChangeCounter/Ciclo1/Test/LOGTEST | Int Test | 0.00625 | 0.0069444 | 0.3% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | TEST1 | Otros interesados | 100% | 107% | 0.3%
/Process Dashboard/ChangeCounter/Ciclo1/Test/User Documentation | Documentation | 0.00625 | 0.013889 | 0.3% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | TEST1 | Otros interesados | 100% | 214% | 0.3%
/Process Dashboard/ChangeCounter/Ciclo1/Design/LOGD | Design | 0.0034722 | 0.0069444 | 0.2% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | DES1 | Otros interesados | 100% | 208% | 0.2%
/Process Dashboard/ChangeCounter/Ciclo1/Postmortem/PEER | Postmortem | 0.0055556 | 0.013889 | 0.3% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 | PM1 | Esperando | 100% | 250% | 0.3%
/Process Dashboard/ChangeCounter/Ciclo1/Postmortem/PIP | Postmortem | 0.0055556 | 0.013889 | 0.3% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 | PM1 | Esperando | 100% | 250% | 0.3%
/Process Dashboard/ChangeCounter/Ciclo1/Postmortem/Cycle Report | Postmortem | 0.0055556 | 0.0069444 | 0.3% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 | PM1 | Esperando | 100% | 125% | 0.3%
/Process Dashboard/ChangeCounter/Ciclo1/Postmortem/Role Report | Postmortem | 0.0055556 | 0.0069444 | 0.3% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 | PM1 | Esperando | 100% | 125% | 0.3%
/Process Dashboard/ChangeCounter/Ciclo1/Postmortem/Engineer Report | Postmortem | 0.0055556 | 0.0055556 | 0.3% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 | PM1 | Esperando | 100% | 100% | 0.3%
/Process Dashboard/ChangeCounter/Ciclo1/Design/Test Devel | Test Devel | 0.020139 | 0.0069444 | 1% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 | DES1 | Otros interesados | 100% | 35% | 1%
/Process Dashboard/ChangeCounter/Ciclo1/Every Week/Product Baseline | Postmortem | 0.010417 | 0.083333 | 0.5% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 |  |  | 100% | 776% | 0.5%
/Process Dashboard/ChangeCounter/Ciclo2/Planning/Personal SCHEDULE | Planning | 0.0041667 | 0.0034722 | 0.2% | 2014-04-08 | 2014-04-16 | 2014-04-16 | 2014-04-16 | Week4 | Otros interesados | 100% | 84% | 0.2%
/Process Dashboard/ChangeCounter/Ciclo2/Planning/Personal TASK | Planning | 0.0027778 | 0.0034722 | 0.1% | 2014-04-08 | 2014-04-16 | 2014-04-16 | 2014-04-16 | Week4 | Otros interesados | 100% | 140% | 0.1%
/Process Dashboard/ChangeCounter/Ciclo2/Every Week4/Data reporting | Postmortem | 0.00069444 | 0.010417 | 0% | 2014-04-08 | 2014-04-16 | 2014-04-16 | 2014-04-16 | Week4 |  | 100% | 1738% | 0%
/Process Dashboard/ChangeCounter/Ciclo2/Every Week4/weekly meeting | Postmortem | 0.020833 | 0.017361 | 1% | 2014-04-08 | 2014-04-16 | 2014-04-16 | 2014-04-16 | Week4 |  | 100% | 83% | 1%
/Process Dashboard/ChangeCounter/Ciclo2/Documentation/Review | Documentation | 0.00625 | 0.25694 | 0.3% | 2014-04-08 | 2014-04-16 | 2014-04-16 | 2014-04-16 | Week7 |  | 100% | 4286% | 0.3%
/Process Dashboard/ChangeCounter/Ciclo2/Documentation/OutLine | Documentation | 0.25 | 0.0034722 | 12.1% | 2014-04-15 | 2014-04-16 | 2014-04-16 | 2014-04-16 | Week7 |  | 100% | 1% | 12.1%
/Process Dashboard/ChangeCounter/Ciclo2/Every Week5/weekly meeting | Postmortem | 0.020833 | 0.010417 | 1% | 2014-04-15 | 2014-04-23 | 2014-04-23 | 2014-04-23 | Week5 |  | 100% | 50% | 1%
/Process Dashboard/ChangeCounter/Ciclo2/Every Week5/Data reporting | Postmortem | 0.00069444 | 0.0034722 | 0% | 2014-04-15 | 2014-04-23 | 2014-04-23 | 2014-04-23 | Week5 |  | 100% | 579% | 0%
/Process Dashboard/ChangeCounter/Ciclo2/Reqts/SRS update Baseline | Reqts Review | 0.041667 | 0.041667 | 2% | 2014-04-15 | 2014-04-23 | 2014-04-23 | 2014-04-23 | Week5 | Otros interesados | 100% | 100% | 2%
/Process Dashboard/ChangeCounter/Ciclo2/Design/LOGD | Design | 0.0027778 | 0.0027778 | 0.1% | 2014-04-15 | 2014-04-23 | 2014-04-23 | 2014-04-23 | Week5 | Otros interesados | 100% | 110% | 0.1%
/Process Dashboard/ChangeCounter/Ciclo2/Design/Design Review | Design Review | 0.0076389 | 0.0069444 | 0.4% | 2014-04-15 | 2014-04-23 | 2014-04-23 | 2014-04-23 | Week5 | Otros interesados | 100% | 91% | 0.4%
/Process Dashboard/ChangeCounter/Ciclo2/Design/Design Inspect | Design Inspect | 0.0027778 | 0.0034722 | 0.1% | 2014-04-15 | 2014-04-23 | 2014-04-23 | 2014-04-23 | Week5 | Otros interesados | 100% | 114% | 0.1%
/Process Dashboard/ChangeCounter/Ciclo2/Every Week6/weekly meeting | Postmortem | 0.020833 | 0.0069444 | 1% | 2014-04-15 | 2014-04-29 | 2014-04-29 | 2014-04-29 | Week6 |  | 100% | 33% | 1%
/Process Dashboard/ChangeCounter/Ciclo2/Every Week6/Data reporting | Postmortem | 0.00069444 | 0.25347 | 0% | 2014-04-15 | 2014-04-29 | 2014-04-29 | 2014-04-29 | Week6 |  | 100% | 42284% | 0%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Implementation/class lineType/Planning | Planning | 0.0034722 | 0.0048611 | 0.2% | 2014-04-15 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 156% | 0.2%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Implementation/class program/Planning | Planning | 0.0076389 | 0.0069444 | 0.4% | 2014-04-15 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 95% | 0.4%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Implementation/class lineType/Design | Design | 0.015972 | 0.013889 | 0.8% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 89% | 0.8%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Implementation/class lineType/Design Review | Design Review | 0.0076389 | 0.0034722 | 0.4% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 44% | 0.4%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Implementation/class lineType/Code | Code | 0.015972 | 0.027778 | 0.8% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 178% | 0.8%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Implementation/class lineType/Code Review | Code Review | 0.0076389 | 0.0069444 | 0.4% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 89% | 0.4%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Implementation/class lineType/Compile | Compile | 0.0013889 | 0 | 0.1% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% |  | 0.1%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Implementation/class lineType/Test | Test | 0.0076389 | 0.0034722 | 0.4% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 44% | 0.4%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Implementation/class lineType/Postmortem | Postmortem | 0.0034722 | 0.0034722 | 0.2% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 111% | 0.2%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Implementation/class program/Design | Design | 0.036806 | 0.013889 | 1.8% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 38% | 1.8%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Implementation/class program/Design Review | Design Review | 0.018056 | 0.0034722 | 0.9% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 19% | 0.9%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Implementation/class program/Code | Code | 0.036806 | 0.10417 | 1.8% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 286% | 1.8%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Implementation/class program/Code Review | Code Review | 0.018056 | 0.0069444 | 0.9% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 38% | 0.9%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Implementation/class program/Compile | Compile | 0.0034722 | 0 | 0.2% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% |  | 0.2%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Implementation/class program/Test | Test | 0.018056 | 0.010417 | 0.9% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 57% | 0.9%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Implementation/class program/Postmortem | Postmortem | 0.0076389 | 0.0034722 | 0.4% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 48% | 0.4%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Code Review | Code Review | 0.083333 | 0.0069444 | 4% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 8% | 4%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Code Inspect | Code Inspect | 0.041667 | 0.0069444 | 2% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 17% | 2%
/Process Dashboard/ChangeCounter/Ciclo2/Code/UpdateLOGD | Code Inspect | 0.0027778 | 0.0034722 | 0.1% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 123% | 0.1%
/Process Dashboard/ChangeCounter/Ciclo2/Code/UpdateLOGT | Code Inspect | 0.0027778 | 0.0034722 | 0.1% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 123% | 0.1%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Unit Test | Test | 0.068056 | 0 | 3.3% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% |  | 3.3%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Component Baseline | Test | 0.083333 | 0.0034722 | 4% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 4% | 4%
/Process Dashboard/ChangeCounter/Ciclo2/Code/Detailed Design | Design | 0.0055556 | 0.010417 | 0.3% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Otros interesados | 100% | 185% | 0.3%
/Process Dashboard/ChangeCounter/Ciclo2/Test/LOGTEST | Int Test | 0.10417 | 0.0013889 | 5% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week6 | Esperando | 100% | 1% | 5%
/Process Dashboard/ChangeCounter/Ciclo2/Test/User Documentation | Documentation | 0.0625 | 0.0034722 | 3% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week6 | Esperando | 100% | 6% | 3%
/Process Dashboard/ChangeCounter/Ciclo2/Postmortem/PEER | Postmortem | 0.0034722 | 0.0034722 | 0.2% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week7 | Completado | 100% | 100% | 0.2%
/Process Dashboard/ChangeCounter/Ciclo2/Postmortem/PIP | Postmortem | 0.0069444 | 0.0034722 | 0.3% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week7 | Completado | 100% | 50% | 0.3%
/Process Dashboard/ChangeCounter/Ciclo2/Postmortem/Role Report | Postmortem | 0.0020833 | 0.0034722 | 0.1% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week7 | Completado | 100% | 167% | 0.1%
/Process Dashboard/ChangeCounter/Ciclo2/Postmortem/Engineer Report | Postmortem | 0.0020833 | 0.0034722 | 0.1% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week7 | Completado | 100% | 167% | 0.1%
/Process Dashboard/ChangeCounter/Ciclo1/Reqts/SRS Baseline | Reqts Review | 0.070139 | 0.0625 | 3.4% | 2014-04-29 | 2014-04-30 | 2014-04-30 | 2014-04-30 | REQ1 | Otros interesados | 100% | 89% | 3.4%
/Process Dashboard/ChangeCounter/Ciclo1/Design/Design Review | Design Review | 0.020139 | 0.020833 | 1% | 2014-04-29 | 2014-04-30 | 2014-04-30 | 2014-04-30 | DES1 | Otros interesados | 100% | 104% | 1%
/Process Dashboard/ChangeCounter/Ciclo1/Code/Code Inspect | Code Inspect | 0.029167 | 0.027778 | 1.4% | 2014-04-29 | 2014-04-30 | 2014-04-30 | 2014-04-30 | IMP1 | Otros interesados | 100% | 95% | 1.4%
/Process Dashboard/ChangeCounter/Ciclo1/Code/Component Baseline | Test | 0.014583 | 0.013889 | 0.7% | 2014-04-29 | 2014-04-30 | 2014-04-30 | 2014-04-30 | IMP1 | Otros interesados | 100% | 95% | 0.7%
/Process Dashboard/ChangeCounter/Ciclo2/Every Week7/weekly meeting | Postmortem | 0.020833 | 0.020833 | 1% | 2014-04-29 | 2014-05-05 | 2014-05-05 | 2014-05-05 | Week7 |  | 100% | 100% | 1%
/Process Dashboard/ChangeCounter/Ciclo2/Every Week7/Data reporting | Postmortem | 0.00069444 | 0.00069444 | 0% | 2014-04-29 | 2014-05-05 | 2014-05-05 | 2014-05-05 | Week7 |  | 100% | 116% | 0%
De | Para | PT | CPT | CPV | Tiempo | CT | VG
2014-03-05 | 2014-03-11 | 0 | 0 | 0% | 0 | 0 | 0%
2014-03-12 | 2014-03-18 | 0.25 | 0.25 | 8% | 0.0069444 | 0.0069444 | 0%
2014-03-19 | 2014-03-25 | 0.25 | 0.5 | 21.3% | 0.041667 | 0.048611 | 0%
2014-03-26 | 2014-04-01 | 0.25 | 0.75 | 33.5% | 0.47222 | 0.52083 | 0%
2014-04-02 | 2014-04-08 | 0.25 | 1899-12-31 | 42.9% | 0.14931 | 0.67014 | 21.3%
2014-04-09 | 2014-04-15 | 0.25 | 1899-12-31 06:00 | 60.2% | 0.59514 | 1899-12-31 06:22 | 41.2%
2014-04-16 | 2014-04-22 | 0.66667 | 1899-12-31 22:00 | 92.5% | 0.10347 | 1899-12-31 08:51 | 55%
2014-04-23 | 2014-04-29 | 0.25 | 1900-01-01 04:00 | 100% | 0.53958 | 1899-12-31 21:48 | 59.7%
2014-04-30 | 2014-05-06 | 0.125 | 1900-01-01 07:00 | 100% | 0.068056 | 1899-12-31 23:26 | 100%
2014-05-07 | 2014-05-13 | END | 1900-01-01 07:00 | 100% | 0 | 1899-12-31 23:26 | 100%