## excel
Planned Completion Date: | 2014-05-06
Replanned Completion Date: | 2014-05-07
Cost Variance: | 10.108 | (10,1 hours under budget)
Cost Variance %: | 19% | (19% under budget)
Cost Performance Index: | 1.233
Schedule Variance: | 0 | (0 minutes ahead of schedule)
Schedule Variance %: | 0% | (0% ahead of schedule)
Schedule Variance Duration: | 0 | (0 minutes ahead of schedule)
Schedule Performance Index: | 1
Percent Complete: | 100%
Percent Spent on Completed Tasks: | 81%
To Complete Performance Index: | 0
Improvement Ratio: | -1
Forecast Cost: | 43.367 | (43,4 hours)
Forecast Duration: | 63.306 | (2,11 months)
Forecast Completion Date: | 2014-05-07
Project/Task | Type | PT | Time | PV | Plan Date | Replan | Forecast | Date | Labels | Dep | %C | %S | EV
/Project/ChangeCounter/Ciclo1/Launch/INFOForm | Misc | 0.16597 | 0.0027778 | 7.4% | 2014-03-18 | 2014-03-31 | 2014-03-31 | 2014-03-31 | LAU1 | Others Interested | 100% | 2% | 7.4%
/Project/ChangeCounter/Ciclo1/Planning/TASK | Planning | 0.080556 | 0.083333 | 3.6% | 2014-03-18 | 2014-03-31 | 2014-03-31 | 2014-03-31 | PLAN1 | Others Interested | 100% | 104% | 3.6%
/Project/ChangeCounter/Ciclo1/Planning/SCHEDULE | Planning | 0.010417 | 0.010417 | 0.5% | 2014-03-25 | 2014-03-31 | 2014-03-31 | 2014-03-31 | PLAN1 | Others Interested | 100% | 97% | 0.5%
/Project/ChangeCounter/Ciclo1/Planning/Personal TASK | Planning | 0.0055556 | 0.0041667 | 0.2% | 2014-03-25 | 2014-03-31 | 2014-03-31 | 2014-03-31 | PLAN1 | Others Interested | 100% | 78% | 0.2%
/Project/ChangeCounter/Ciclo1/Planning/Personal SCHEDULE | Planning | 0.0055556 | 0.0048611 | 0.2% | 2014-03-25 | 2014-03-31 | 2014-03-31 | 2014-03-31 | PLAN1 | Others Interested | 100% | 91% | 0.2%
/Project/ChangeCounter/Ciclo1/Planning/SUMP | Planning | 0.031944 | 0.041667 | 1.4% | 2014-03-25 | 2014-03-31 | 2014-03-31 | 2014-03-31 | PLAN1 | Others Interested | 100% | 129% | 1.4%
/Project/ChangeCounter/Ciclo1/Planning/SUMTASK | Planning | 0.010417 | 0.020833 | 0.5% | 2014-03-25 | 2014-03-31 | 2014-03-31 | 2014-03-31 | PLAN1 | Others Interested | 100% | 194% | 0.5%
/Project/ChangeCounter/Ciclo1/Planning/Balance TASK | Planning | 0.010417 | 0.03125 | 0.5% | 2014-03-25 | 2014-03-31 | 2014-03-31 | 2014-03-31 | PLAN1 | Others Interested | 100% | 291% | 0.5%
/Project/ChangeCounter/Ciclo1/Planning/Balance SCHEDULE | Planning | 0.010417 | 0.027778 | 0.5% | 2014-03-25 | 2014-03-31 | 2014-03-31 | 2014-03-31 | PLAN1 | Others Interested | 100% | 259% | 0.5%
/Project/ChangeCounter/Ciclo1/Strategy/STRAT | Strategy | 0.05625 | 0.052083 | 2.5% | 2014-03-25 | 2014-04-01 | 2014-04-01 | 2014-04-01 | STRAT1 | Waiting | 100% | 93% | 2.5%
/Project/ChangeCounter/Ciclo1/Planning/SUMS | Planning | 0.080556 | 0.058333 | 3.6% | 2014-03-25 | 2014-04-01 | 2014-04-01 | 2014-04-01 | PLAN1 | Others Interested | 100% | 72% | 3.6%
/Project/ChangeCounter/Ciclo1/Design/Design Review | Design Review | 0.020139 | 0.013889 | 0.9% | 2014-03-25 | 2014-04-01 | 2014-04-01 | 2014-04-01 | DES1 | Others Interested | 100% | 69% | 0.9%
/Project/ChangeCounter/Ciclo1/Design/UpdateSUMP | Design | 0.040278 | 0.027778 | 1.8% | 2014-04-01 | 2014-04-01 | 2014-04-01 | 2014-04-01 | DES1 | Others Interested | 100% | 69% | 1.8%
/Project/ChangeCounter/Ciclo1/Reqts/SRS | Reqts Review | 0.035417 | 0.038889 | 1.6% | 2014-04-01 | 2014-04-01 | 2014-04-01 | 2014-04-01 | REQ1 | Others Interested | 100% | 111% | 1.6%
/Project/ChangeCounter/Ciclo1/Design/LOGD | Design | 0.0034722 | 0.0013889 | 0.1% | 2014-04-01 | 2014-04-09 | 2014-04-09 | 2014-04-09 | DES1 | Others Interested | 100% | 42% | 0.1%
/Project/ChangeCounter/Ciclo1/Design/Test Devel | Test Devel | 0.020139 | 0.022222 | 0.9% | 2014-04-01 | 2014-04-09 | 2014-04-09 | 2014-04-09 | DES1 | Others Interested | 100% | 111% | 0.9%
/Project/ChangeCounter/Ciclo1/Design/Design Inspect | Design Inspect | 0.040278 | 0.03125 | 1.8% | 2014-04-01 | 2014-04-09 | 2014-04-09 | 2014-04-09 | DES1 | Others Interested | 100% | 78% | 1.8%
/Project/ChangeCounter/Ciclo1/Code/Implementation Standards | Code | 0.014583 | 0.013889 | 0.7% | 2014-04-01 | 2014-04-09 | 2014-04-09 | 2014-04-09 | IMP1 | Others Interested | 100% | 95% | 0.7%
/Project/ChangeCounter/Ciclo1/Code/Detailed Design | Design | 0.0048611 | 0.0125 | 0.2% | 2014-04-01 | 2014-04-09 | 2014-04-09 | 2014-04-09 | IMP1 | Others Interested | 100% | 245% | 0.2%
/Project/ChangeCounter/Ciclo1/Code/Implementation | Code | 0.11667 | 0.24167 | 5.2% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | IMP1 | Others Interested | 100% | 207% | 5.2%
/Project/ChangeCounter/Ciclo1/Code/Code Review | Code Review | 0.058333 | 0.10417 | 2.6% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | IMP1 | Others Interested | 100% | 179% | 2.6%
/Project/ChangeCounter/Ciclo1/Code/Code Inspect | Code Inspect | 0.029167 | 0.027778 | 1.3% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | IMP1 | Others Interested | 100% | 95% | 1.3%
/Project/ChangeCounter/Ciclo1/Code/UpdateSUMP | Code Inspect | 0.011806 | 0.034722 | 0.5% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | IMP1 | Others Interested | 100% | 298% | 0.5%
/Project/ChangeCounter/Ciclo1/Code/UpdateLOGD | Code Inspect | 0.0020833 | 0.0048611 | 0.1% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | IMP1 | Others Interested | 100% | 200% | 0.1%
/Project/ChangeCounter/Ciclo1/Code/UpdateLOGT | Code Inspect | 0.0020833 | 0.0069444 | 0.1% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | IMP1 | Others Interested | 100% | 286% | 0.1%
/Project/ChangeCounter/Ciclo1/Code/Unit Test | Test | 0.0090278 | 0.055556 | 0.4% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | IMP1 | Others Interested | 100% | 635% | 0.4%
/Project/ChangeCounter/Ciclo1/Test/Sys Test | Sys Test | 0.00625 | 0.0069444 | 0.3% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | TEST1 | Others Interested | 100% | 107% | 0.3%
/Project/ChangeCounter/Ciclo1/Test/Int Test | Int Test | 0.00625 | 0.0034722 | 0.3% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | TEST1 | Waiting | 100% | 54% | 0.3%
/Project/ChangeCounter/Ciclo1/Test/LOGTEST | Int Test | 0.00625 | 0.0083333 | 0.3% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | TEST1 | Others Interested | 100% | 129% | 0.3%
/Project/ChangeCounter/Ciclo1/Test/User Documentation | Documentation | 0.00625 | 0.0090278 | 0.3% | 2014-04-08 | 2014-04-09 | 2014-04-09 | 2014-04-09 | TEST1 | Others Interested | 100% | 139% | 0.3%
/Project/ChangeCounter/Ciclo1/Documentation/Review | Documentation | 0.011111 | 0.0090278 | 0.5% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 |  |  | 100% | 80% | 0.5%
/Project/ChangeCounter/Ciclo1/Every Week/Weekly report | Postmortem | 0.010417 | 0.025 | 0.5% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 |  |  | 100% | 233% | 0.5%
/Project/ChangeCounter/Ciclo1/Every Week/Weekly analysis | Postmortem | 0.010417 | 0.010417 | 0.5% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 |  |  | 100% | 97% | 0.5%
/Project/ChangeCounter/Ciclo1/Every Week/Data reporting | Postmortem | 0.0055556 | 0.0069444 | 0.2% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 |  |  | 100% | 129% | 0.2%
/Project/ChangeCounter/Ciclo1/Every Week/weekly meeting | Postmortem | 0.011806 | 0.083333 | 0.5% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 |  |  | 100% | 724% | 0.5%
/Project/ChangeCounter/Ciclo1/Postmortem/PEER | Postmortem | 0.0055556 | 0.0027778 | 0.2% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 | PM1 | Waiting | 100% | 50% | 0.2%
/Project/ChangeCounter/Ciclo1/Postmortem/PIP | Postmortem | 0.0055556 | 0.0034722 | 0.2% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 | PM1 | Waiting | 100% | 62% | 0.2%
/Project/ChangeCounter/Ciclo1/Postmortem/Cycle Report | Postmortem | 0.0055556 | 0.0083333 | 0.2% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 | PM1 | Waiting | 100% | 150% | 0.2%
/Project/ChangeCounter/Ciclo1/Postmortem/Role Report | Postmortem | 0.0055556 | 0.0048611 | 0.2% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 | PM1 | Waiting | 100% | 88% | 0.2%
/Project/ChangeCounter/Ciclo1/Postmortem/Engineer Report | Postmortem | 0.0055556 | 0.0034722 | 0.2% | 2014-04-08 | 2014-04-14 | 2014-04-14 | 2014-04-14 | PM1 | Waiting | 100% | 62% | 0.2%
/Project/ChangeCounter/Ciclo2/Strategy/STRAT | Strategy | 0.052778 | 0.034722 | 2.4% | 2014-04-15 | 2014-04-16 | 2014-04-16 | 2014-04-16 | Week4 | Others Interested | 100% | 66% | 2.4%
/Project/ChangeCounter/Ciclo2/Planning/SUMS | Planning | 0.025 | 0.010417 | 1.1% | 2014-04-15 | 2014-04-16 | 2014-04-16 | 2014-04-16 | Week4 | Others Interested | 100% | 42% | 1.1%
/Project/ChangeCounter/Ciclo2/Planning/TASK | Planning | 0.025 | 0.013889 | 1.1% | 2014-04-15 | 2014-04-16 | 2014-04-16 | 2014-04-16 | Week4 | Others Interested | 100% | 56% | 1.1%
/Project/ChangeCounter/Ciclo2/Planning/SCHEDULE | Planning | 0.025 | 0.027778 | 1.1% | 2014-04-15 | 2014-04-16 | 2014-04-16 | 2014-04-16 | Week4 | Others Interested | 100% | 112% | 1.1%
/Project/ChangeCounter/Ciclo2/Planning/SUMP | Planning | 0.025 | 0.020833 | 1.1% | 2014-04-15 | 2014-04-16 | 2014-04-16 | 2014-04-16 | Week4 | Others Interested | 100% | 84% | 1.1%
/Project/ChangeCounter/Ciclo2/Planning/Personal TASK | Planning | 0.0027778 | 0.0069444 | 0.1% | 2014-04-15 | 2014-04-16 | 2014-04-16 | 2014-04-16 | Week4 | Others Interested | 100% | 281% | 0.1%
/Project/ChangeCounter/Ciclo2/Planning/Personal SCHEDULE | Planning | 0.0041667 | 0.0090278 | 0.2% | 2014-04-15 | 2014-04-16 | 2014-04-16 | 2014-04-16 | Week4 | Others Interested | 100% | 219% | 0.2%
/Project/ChangeCounter/Ciclo2/Planning/Balance TASK | Planning | 0.025 | 0.010417 | 1.1% | 2014-04-15 | 2014-04-16 | 2014-04-16 | 2014-04-16 | Week4 | Others Interested | 100% | 42% | 1.1%
/Project/ChangeCounter/Ciclo2/Planning/Balance SCHEDULE | Planning | 0.025 | 0.013194 | 1.1% | 2014-04-15 | 2014-04-16 | 2014-04-16 | 2014-04-16 | Week4 | Others Interested | 100% | 53% | 1.1%
/Project/ChangeCounter/Ciclo2/Every Week4/weekly meeting | Postmortem | 0.020833 | 0.013889 | 0.9% | 2014-04-15 | 2014-04-20 | 2014-04-20 | 2014-04-20 | Week4 |  | 100% | 67% | 0.9%
/Project/ChangeCounter/Ciclo2/Every Week4/Weekly report | Postmortem | 0.0034722 | 0.0069444 | 0.2% | 2014-04-15 | 2014-04-20 | 2014-04-20 | 2014-04-20 | Week4 |  | 100% | 193% | 0.2%
/Project/ChangeCounter/Ciclo2/Every Week4/Weekly analysis | Postmortem | 0.0034722 | 0.0020833 | 0.2% | 2014-04-15 | 2014-04-20 | 2014-04-20 | 2014-04-20 | Week4 |  | 100% | 58% | 0.2%
/Project/ChangeCounter/Ciclo2/Every Week4/Data reporting | Postmortem | 0.00069444 | 0.00069444 | 0% | 2014-04-15 | 2014-04-20 | 2014-04-20 | 2014-04-20 | Week4 |  | 100% | 116% | 0%
/Project/ChangeCounter/Ciclo2/Design/LOGD | Design | 0.0027778 | 0.00069444 | 0.1% | 2014-04-15 | 2014-04-22 | 2014-04-22 | 2014-04-22 | Week5 | Others Interested | 100% | 27% | 0.1%
/Project/ChangeCounter/Ciclo2/Design/UpdateSUMP | Design | 0.0027778 | 0.0034722 | 0.1% | 2014-04-15 | 2014-04-22 | 2014-04-22 | 2014-04-22 | Week5 | Others Interested | 100% | 114% | 0.1%
/Project/ChangeCounter/Ciclo2/Design/Design Review | Design Review | 0.0076389 | 0.0069444 | 0.3% | 2014-04-15 | 2014-04-22 | 2014-04-22 | 2014-04-22 | Week5 | Others Interested | 100% | 91% | 0.3%
/Project/ChangeCounter/Ciclo2/Every Week5/weekly meeting | Postmortem | 0.020833 | 0.0041667 | 0.9% | 2014-04-22 | 2014-04-22 | 2014-04-22 | 2014-04-22 | Week5 |  | 100% | 20% | 0.9%
/Project/ChangeCounter/Ciclo2/Every Week5/Weekly report | Postmortem | 0.041667 | 0.0034722 | 1.9% | 2014-04-22 | 2014-04-22 | 2014-04-22 | 2014-04-22 | Week5 |  | 100% | 8% | 1.9%
/Project/ChangeCounter/Ciclo2/Every Week5/Weekly analysis | Postmortem | 0.020833 | 0.0034722 | 0.9% | 2014-04-22 | 2014-04-22 | 2014-04-22 | 2014-04-22 | Week5 |  | 100% | 17% | 0.9%
/Project/ChangeCounter/Ciclo2/Every Week5/Data reporting | Postmortem | 0.00069444 | 0.00069444 | 0% | 2014-04-22 | 2014-04-22 | 2014-04-22 | 2014-04-22 | Week5 |  | 100% | 116% | 0%
/Project/ChangeCounter/Ciclo2/Code/Implementation/class panelInputVersion/Planning | Planning | 0.0097222 | 0.00625 | 0.4% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 67% | 0.4%
/Project/ChangeCounter/Ciclo2/Code/Implementation/class panelInputVersion/Design | Design | 0.047222 | 0.016667 | 2.1% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 36% | 2.1%
/Project/ChangeCounter/Ciclo2/Code/Implementation/class panelInputVersion/Design Review | Design Review | 0.023611 | 0.011111 | 1.1% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 47% | 1.1%
/Project/ChangeCounter/Ciclo2/Code/Implementation/class panelInputVersion/Code | Code | 0.047222 | 0.057639 | 2.1% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 123% | 2.1%
/Project/ChangeCounter/Ciclo2/Code/Implementation/class panelInputVersion/Code Review | Code Review | 0.023611 | 0.019444 | 1.1% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 83% | 1.1%
/Project/ChangeCounter/Ciclo2/Code/Implementation/class panelInputVersion/Compile | Compile | 0.0048611 | 0 | 0.2% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% |  | 0.2%
/Project/ChangeCounter/Ciclo2/Code/Implementation/class panelInputVersion/Test | Test | 0.023611 | 0.0125 | 1.1% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 53% | 1.1%
/Project/ChangeCounter/Ciclo2/Code/Implementation/class panelInputVersion/Postmortem | Postmortem | 0.0097222 | 0.0076389 | 0.4% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 81% | 0.4%
/Project/ChangeCounter/Ciclo2/Code/Implementation/Actualizacion de clases/Planning | Planning | 0.0013889 | 0.0055556 | 0.1% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 336% | 0.1%
/Project/ChangeCounter/Ciclo2/Code/Implementation/Actualizacion de clases/Design | Design | 0.0041667 | 0.0020833 | 0.2% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 47% | 0.2%
/Project/ChangeCounter/Ciclo2/Code/Implementation/Actualizacion de clases/Design Review | Design Review | 0.0027778 | 0.0020833 | 0.1% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 71% | 0.1%
/Project/ChangeCounter/Ciclo2/Code/Implementation/Actualizacion de clases/Code | Code | 0.015278 | 0.0083333 | 0.7% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 55% | 0.7%
/Project/ChangeCounter/Ciclo2/Code/Implementation/Actualizacion de clases/Code Review | Code Review | 0.0048611 | 0.0069444 | 0.2% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 135% | 0.2%
/Project/ChangeCounter/Ciclo2/Code/Implementation/Actualizacion de clases/Compile | Compile | 0 | 0 | 0% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% |  | 0%
/Project/ChangeCounter/Ciclo2/Code/Implementation/Actualizacion de clases/Test | Test | 0.0034722 | 0.0034722 | 0.1% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 105% | 0.1%
/Project/ChangeCounter/Ciclo2/Code/Implementation/Actualizacion de clases/Postmortem | Postmortem | 0.0020833 | 0.010417 | 0.1% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 515% | 0.1%
/Project/ChangeCounter/Ciclo2/Code/Detailed Design | Design | 0.0055556 | 0.0034722 | 0.3% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 62% | 0.3%
/Project/ChangeCounter/Ciclo2/Code/Code Review | Code Review | 0.083333 | 0.052778 | 3.7% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 63% | 3.7%
/Project/ChangeCounter/Ciclo2/Code/Code Inspect | Code Inspect | 0.041667 | 0.029861 | 1.9% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 72% | 1.9%
/Project/ChangeCounter/Ciclo2/Code/UpdateSUMP | Code Inspect | 0.10417 | 0.013889 | 4.7% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 13% | 4.7%
/Project/ChangeCounter/Ciclo2/Code/UpdateLOGD | Code Inspect | 0.0027778 | 0.0013889 | 0.1% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 49% | 0.1%
/Project/ChangeCounter/Ciclo2/Code/UpdateLOGT | Code Inspect | 0.0027778 | 0.0097222 | 0.1% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 345% | 0.1%
/Project/ChangeCounter/Ciclo2/Code/Unit Test | Test | 0.068056 | 0.0090278 | 3% | 2014-04-22 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week5 | Others Interested | 100% | 13% | 3%
/Project/ChangeCounter/Ciclo2/Test/LOGTEST | Int Test | 0.10417 | 0.0125 | 4.7% | 2014-04-29 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week6 | Waiting | 100% | 12% | 4.7%
/Project/ChangeCounter/Ciclo2/Every Week6/Data reporting | Postmortem | 0.00069444 | 0.00069444 | 0% | 2014-04-29 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week6 |  | 100% | 116% | 0%
/Project/ChangeCounter/Ciclo2/Every Week6/weekly meeting | Postmortem | 0.020833 | 0.019444 | 0.9% | 2014-04-29 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week6 |  | 100% | 93% | 0.9%
/Project/ChangeCounter/Ciclo2/Every Week6/Weekly report | Postmortem | 0.041667 | 0.013889 | 1.9% | 2014-04-29 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week6 |  | 100% | 33% | 1.9%
/Project/ChangeCounter/Ciclo2/Every Week6/Weekly analysis | Postmortem | 0.041667 | 0.0041667 | 1.9% | 2014-04-29 | 2014-04-30 | 2014-04-30 | 2014-04-30 | Week6 |  | 100% | 10% | 1.9%
/Project/ChangeCounter/Ciclo2/Postmortem/Engineer Report | Postmortem | 0.0020833 | 0.0069444 | 0.1% | 2014-04-29 | 2014-05-07 | 2014-05-07 | 2014-05-07 | Week7 | Complete | 100% | 333% | 0.1%
/Project/ChangeCounter/Ciclo2/Postmortem/PEER | Postmortem | 0.0034722 | 0.0027778 | 0.2% | 2014-04-29 | 2014-05-07 | 2014-05-07 | 2014-05-07 | Week7 | Complete | 100% | 80% | 0.2%
/Project/ChangeCounter/Ciclo2/Postmortem/PIP | Postmortem | 0.0069444 | 0.00625 | 0.3% | 2014-04-29 | 2014-05-07 | 2014-05-07 | 2014-05-07 | Week7 | Complete | 100% | 90% | 0.3%
/Project/ChangeCounter/Ciclo2/Postmortem/Cycle Report | Postmortem | 0.025 | 0.024306 | 1.1% | 2014-04-29 | 2014-05-07 | 2014-05-07 | 2014-05-07 | Week7 | Complete | 100% | 97% | 1.1%
/Project/ChangeCounter/Ciclo2/Postmortem/Role Report | Postmortem | 0.0020833 | 0.0027778 | 0.1% | 2014-04-29 | 2014-05-07 | 2014-05-07 | 2014-05-07 | Week7 | Complete | 100% | 133% | 0.1%
/Project/ChangeCounter/Ciclo2/Documentation/Review | Documentation | 0.03125 | 0.027778 | 1.4% | 2014-04-29 | 2014-05-07 | 2014-05-07 | 2014-05-07 | Week7 |  | 100% | 89% | 1.4%
/Project/ChangeCounter/Ciclo2/Every Week7/Weekly analysis | Postmortem | 0.041667 | 0.015972 | 1.9% | 2014-04-29 | 2014-05-07 | 2014-05-07 | 2014-05-07 | Week7 |  | 100% | 38% | 1.9%
/Project/ChangeCounter/Ciclo2/Every Week7/Data reporting | Postmortem | 0.00069444 | 0.00069444 | 0% | 2014-04-29 | 2014-05-07 | 2014-05-07 | 2014-05-07 | Week7 |  | 100% | 116% | 0%
/Project/ChangeCounter/Ciclo2/Every Week7/weekly meeting | Postmortem | 0.020833 | 0.010417 | 0.9% | 2014-05-06 | 2014-05-07 | 2014-05-07 | 2014-05-07 | Week7 |  | 100% | 50% | 0.9%
/Project/ChangeCounter/Ciclo2/Every Week7/Weekly report | Postmortem | 0.041667 | 0.013889 | 1.9% | 2014-05-06 | 2014-05-07 | 2014-05-07 | 2014-05-07 | Week7 |  | 100% | 33% | 1.9%
From | To | PT | CPT | CPV | Time | CT | EV
2014-03-05 | 2014-03-11 | 0 | 0 | 0% | 0 | 0 | 0%
2014-03-12 | 2014-03-18 | 0.25 | 0.25 | 11.1% | 0.0375 | 0.0375 | 0%
2014-03-19 | 2014-03-25 | 0.25 | 0.5 | 21.9% | 0.15625 | 0.19375 | 0%
2014-03-26 | 2014-04-01 | 0.25 | 0.75 | 29% | 0.32222 | 0.51597 | 25.3%
2014-04-02 | 2014-04-08 | 0.25 | 1899-12-31 | 44% | 0.55486 | 1899-12-31 01:42 | 25.3%
2014-04-09 | 2014-04-15 | 0.25 | 1899-12-31 06:00 | 55.2% | 0.12431 | 1899-12-31 04:41 | 44%
2014-04-16 | 2014-04-22 | 0.66667 | 1899-12-31 22:00 | 82.7% | 0.15139 | 1899-12-31 08:19 | 58.9%
2014-04-23 | 2014-04-29 | 0.25 | 1900-01-01 04:00 | 97.2% | 0.30764 | 1899-12-31 15:42 | 58.9%
2014-04-30 | 2014-05-06 | 0.125 | 1900-01-01 07:00 | 100% | 0.08125 | 1899-12-31 17:39 | 92.1%
2014-05-07 | 2014-05-13 | END | 1900-01-01 07:00 | 100% | 0.071528 | 1899-12-31 19:22 | 100%